## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Environment Setup: Python, SQLite, and Threading Libraries | MUST HAVE | No Dependency | Jeyathakseena Ramanathan | 3- Completed
S1 | S1 | US-002 | Introduction to Multithreading Concepts and Practice | MUST HAVE | No Dependency | Abinaya K | 3- Completed
S1 | S1 | US-003 | Project Kickoff: Plan Text Types and Processing Architecture | MUST HAVE | No Dependency | Lithiyasree R | 3- Completed
S2 | S2 | US-004 | Implement Thread Pool for Parallel Text Chunking | MUST HAVE | Python threading module | Jeyathakseena Ramanathan | 3- Completed
S2 | S2 | US-005 | Build Text Loader with Regex-based Preprocessing Filters | MUST HAVE | re module | Abinaya K | 3- Completed
S2 | S2 | US-006 | Test Loader with Large Text Datasets | SHOULD HAVE | US-004, US-005 | Lithiyasree R | 3- Completed
S3 | S3 | US-007 | Design and Implement Rule-Based Sentiment Scoring Logic | MUST HAVE | No Dependency | Jeyathakseena Ramanathan | 3- Completed
S3 | S3 | US-008 | Store Scored Results in SQLite with Retrieval Support | MUST HAVE | SQLite | Abinaya K | 3- Completed
S3 | S3 | US-009 | Build Search Interface and CSV Export Feature | SHOULD HAVE | US-008 | Lithiyasree R | 3- Completed
S3 | S3 | US-010 | Configure Email Summary Alerts on Batch Completion | COULD HAVE | smtplib | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | 3- Completed
S4 | S4 | US-011 | Build and Maintain Inverted Index for Text Search | MUST HAVE | US-008 | Jeyathakseena Ramanathan | 3- Completed
S4 | S4 | US-012 | Performance Testing on Large Text Batches | MUST HAVE | No Dependency | Abinaya K | 3- Completed
S4 | S4 | US-013 | Final Integration, Code Review and Documentation | MUST HAVE | All Modules | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 66 | 6 | 8 | 12 | 12 | 11 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Environment Setup: Python, SQLite, Threading Libraries | 2026-02-09 | 2026-02-11 | Jeyathakseena Ramanathan | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Study Multithreading: ThreadPoolExecutor and Locks | 2026-02-10 | 2026-02-13 | Abinaya K | Others | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | Plan Text Types and Architecture Document | 2026-02-12 | 2026-02-14 | Lithiyasree R | Design | 3- Completed | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 4 | Agile Template and Project Document Discussion | 2026-02-16 | 2026-02-18 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 5 | Finalize Sprint 1 Deliverables and Review | 2026-02-19 | 2026-02-21 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-004 | 6 | Implement Thread Pool for Parallel Chunking | 2026-02-23 | 2026-02-27 | Jeyathakseena Ramanathan | Coding | 3- Completed | 6 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 7 | Build Regex-based Text Preprocessing Filters | 2026-02-23 | 2026-02-26 | Abinaya K | Coding | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 8 | Integrate Loader with Thread Pool and Test | 2026-02-27 | 2026-03-04 | Lithiyasree R | Build | 3- Completed | 5 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 9 | Test Loader on Large Text Datasets and Fix Bugs | 2026-03-04 | 2026-03-07 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | System Test | 3- Completed | 4 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-007 | 10 | Design Sentiment Scoring Rule Set | 2026-03-09 | 2026-03-12 | Jeyathakseena Ramanathan | Design | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 11 | Implement Rule-Based Scorer in Parallel Tasks | 2026-03-11 | 2026-03-14 | Abinaya K | Coding | 3- Completed | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 12 | Store Scored Results in SQLite Database | 2026-03-12 | 2026-03-16 | Lithiyasree R | Coding | 3- Completed | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 13 | Build Search Interface and CSV Export | 2026-03-16 | 2026-03-18 | Jeyathakseena Ramanathan | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 14 | Configure Email Summary Alert Module | 2026-03-18 | 2026-03-19 | Abinaya K | Integration Test | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-011 | 15 | Build Inverted Index for Text Search | 2026-03-20 | 2026-03-23 | Lithiyasree R | Build | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 16 | Maintain and Update Index on New Text Input | 2026-03-23 | 2026-03-25 | Jeyathakseena Ramanathan | Coding | 3- Completed | 3 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 17 | Performance Testing on Large Batch Text Sets | 2026-03-24 | 2026-03-26 | Abinaya K | System Test | 3- Completed | 3 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 18 | Final Integration, Code Review and Documentation | 2026-03-26 | 2026-03-28 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | Others | 3- Completed | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Confusion about project scope and text processing architecture | Held a kickoff discussion with mentor to align on project goals and plan
Sprint 1 | Day 4 | Difficulty understanding Python ThreadPoolExecutor behaviour | Studied official docs and ran small threading experiments together as a team
Sprint 2 | Day 6 | Regex filters not handling all edge cases in raw text input | Reviewed test cases together and updated regex patterns collaboratively
Sprint 2 | Day 8 | Thread pool giving inconsistent chunk sizes on large files | Debugged together, added chunk size normalization logic
Sprint 3 | Day 12 | Difficulty designing scoring rules to produce accurate sentiment labels | Reviewed rule-based NLP examples, revised scoring thresholds as a team
Sprint 3 | Day 14 | SQLite retrieval queries returning partial results | Fixed query conditions and added indexing to improve lookup accuracy
Sprint 4 | Day 17 | Performance dropped on large batch text sets during final testing | Profiled the code, reduced thread contention, improved execution time

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-09 | 2026-02-21 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | Regular milestone reviews and documentation updates | Skipping architecture planning before coding | Team collaboration and knowledge sharing sessions | Conducted detailed architecture planning session before Sprint 2 coding began
2 | Sprint 2 | 2026-02-23 | 2026-03-07 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | Writing unit tests alongside feature development | Merging code without peer review | Parallel task assignment across all three members | Introduced a peer review step before finalizing each module
3 | Sprint 3 | 2026-03-09 | 2026-03-19 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | Validating sentiment scoring rules with diverse text samples | Rushing through rule design without enough test cases | Frequent stand-up syncs to flag blockers early | Added a dedicated rule validation round before integration; improved accuracy
4 | Sprint 4 | 2026-03-20 | 2026-03-28 | Jeyathakseena Ramanathan, Abinaya K, Lithiyasree R | Running performance benchmarks before final submission | Leaving documentation to the last day | Supporting each other when debugging complex issues | Completed all documentation in parallel with final testing; submitted on time
5
6
7